## Time Sheet
Screen Name | UI Design | API Integration | Sonar Qube | Status
Overall Summary | Done | Done | No open issues (last scan) | Completed
Location Summary | Done | Done | No open issues (last scan) | Completed
Location Details | Done | Done | No open issues (last scan) | Completed
Location Insight | Done | Done | No open issues (last scan) | Completed
Daily PRJ | Done | Done | No open issues (last scan) | Completed
Consumption Analysis | Done | Done | No open issues (last scan) | Completed
Stock on Hand | Done | Done | No open issues (last scan) | Completed
Data Tracker Report | Done | Done | No open issues (last scan) | Completed
Target PRJ | Done | Done | No open issues (last scan) | Completed
Productivity | Done | Done | No open issues (last scan) | Completed
Report | Done | Done | No open issues (last scan) | Completed
Category Analysis | Done | Done | No open issues (last scan) | Completed
Item Analysis | Done | Done | No open issues (last scan) | Completed
Item Breakup | Done | Done | No open issues (last scan) | Completed
WasteCost Analysis | Done | On hold (backend team) | No open issues (last scan) | On hold
User Master | Done | Done | No open issues (last scan) | Completed
Location Rights | Done | Done | No open issues (last scan) | Completed
Screen Rights | Placeholder page | Pending (backend API not available) | No open issues (last scan) | Pending
User Log | Done | Done | No open issues (last scan) | Completed
Month Closing | Done | On hold (backend team) | No open issues (last scan) | On hold
General Settings | Done | Not applicable (no API) | No open issues (last scan) | Completed
Login / Logout | Done | Done | No open issues (last scan) | Completed

## Sonar Qube
Metric | Value | Detail | Rating
Security | 0 | Open issues | A
Reliability | 0 | Open issues | A
Maintainability | 0 | Open issues | A
Accepted issues | 28 | Valid issues that were not fixed | -
Coverage | 73% | On 2.1k lines to cover | -
Duplications | 8.0% | On 36k lines | -
Security Hotspots | 12 | Hotspots | E
New Code (quality gate) | Re-check | Last seen: 3 failed - check the dashboard after this scan | -